## RICs
ID | Description | Type | Date Identified | Impact | Probability | Importance | Response | Owner | Closure Date
1 | No development servers provided by I.S | Risk | 2020-01-20 | 200 | Medium | 100 | look into using alternative servers to use as a platform | Tolu | 2020-01-20
2 | lose of project data | Risk | 2020-01-28 | 200 | Very Low | 20 | github repository created | Jon | 2020-01-28
3 | code for live Projex not accessible | Issue | 2020-01-23 | 200 |  | 200 | Mentioned to Brian in PM forum and sponser meeting. Failing that look into doing fresh Projex build with teams own code. *RESOLVED* | Karen | 2020-01-28
4 | understanding/training on python code for projex | Issue | 2020-01-20 | 100 |  | 100 | Training websites used by Brian to create live projex provided to be looked at by the team | Jon, Karen, Tolu, Greg, Nick | 2020-01-23
5 | Room is unavailable for group meeting | Issue | 2020-02-04 | 50 |  | 50 | Try to find another room or location to hold a meeting, even if it is just a quick 15 minute scrum. Failing that keep contact on Slack group chat. | Jon | 2020-02-04
6 | Room is unavailable for sponsor meeting | Issue | 2020-02-04 | 50 |  | 50 | Contact Brain to see if another time or date is suitable for Brain to hold a sponsor meeting. Failling that send an email with the 3 answers for the questions he asks in the meeting - What have you done? What will you do? Any obsticles?- from each team member. | Jon | 2020-02-04
7 | Servers do not function as required due to external factors. | Risk | 2020-02-04 | 200 | Very Low | 20 | Contact I.S to find out what the issue is and for an eta for the solution to be rectified. Set up a alternate server system for short term use if the servers will be down for an extended time. | Jon, Tolu | 2020-02-04
8 | Team members have assignments to do other than group project dividing their time. | Issue | 2020-02-04 | 25 |  | 25 | Try to plan the work load in advance for when the assignments are due so team members do not feel overburdened. Encourage team members to not leave any work until the last minute. | Jon, Karen, Tolu, Greg, Nick | 2020-02-04
9 | Team members have personal issues that make them unavailable to do work. | Issue | 2020-02-04 | 25 |  | 25 | Adjust the projects development where possible. Where possible get another team member to do the work if it is essential for projects progress. | Jon, Karen, Tolu, Greg, Nick | 2020-02-04
10 | Project development goes beyond agreed deadline/handover. | Risk | 2020-02-04 | 200 | Low | 60 | If project development looks like it will not reach completion before deadline/handover contact Brian to discuss extension possiblities. | Jon, Karen, Tolu, Greg, Nick | 2020-02-04
11 | Features not being able to be met within timeframe set for project | Issue | 2020-02-05 | 100 |  | 100 | Prioritise features so main website feature requirements are met first to have least impact on the projects overall functionality. | Jon, Karen, Tolu, Greg, Nick | 2020-02-05
12 | Schedule Timeline not being adhered to | Risk | 2020-02-05 | 100 | Medium | 50 | As we are working in a scrum team within an agile work environment, we can pick up quickly if the scheduling isnt working and either reassess the schedule or agree to commit more hours per week to the project. | Jon, Karen, Tolu, Greg, Nick | 2020-02-05
13 | a conflict in the code that is causing the entire project to not compile | Risk | 2020-02-05 | 150 | Low | 45 | as we are using an online repository we can roll the code back to a previous version | jon, Gregriore | 2020-02-05
14 | disputes between 2 or more group members on how to best approach a feature/task | Issue | 2020-02-05 | 25 |  | 25 | agree in advance that if as a group we cant decide on the best way to approach a certain part of the project we put it to a vote and go with the majority regardless of the personal feelings on the project. | Jon, Karen, Tolu, Greg, Nick | 2020-02-05
15 | different memebers of the group having different styles of writing code | Issue | 2020-02-05 | 25 |  | 25 | The group have agreed in advice a set of coding convention and have them laid out in CONTRIBUTING.md file in the group github for the group to refer to keep coding conventions to a uniform standard throughout the project. | Jon, Karen, Tolu, Greg, Nick | 2020-02-05